## Slide 1
CampusEats – Skip the Lunch Queue (UIU Smart Canteen)
Sprint 1 & 2 Progress Update (2-Week Milestone) | Course: DBMS Lab (CSE) | Live Demo: campus-eats-gamma.vercel.app
Team: Fokir Mostakim Billa Sobuj (Lead), Reduan, Tahmid, Rafiu, Farjana
Course Faculty: Md. Golam Hossain
1. Progress Made (Week 1 & 2)
✓ Week 1: Database & Authentication: • Relational schema designed & hosted on Railway MySQL. • Populated with 139+ authentic UIU canteen dishes across 3 active cafeterias (Khan's, Olympia, Neptune). • User Registration & Login with Bcrypt password hashing (10 salt rounds) and JWT verification. ✓ Week 2: Ordering, Compare & Reviews: • Interactive Food Cart with dynamic daily spending limit guardrails for students. • Pre-order scheduling with custom requested pickup time. • Cross-Canteen Food Comparison Tray: Side-by-side comparison of price, prep-time & ratings. • Dish Review & Star Rating system linked with user orders. ✓ Live Cloud Deployment: • Frontend deployed on Vercel & Backend API live on Render.
2. Blockers & Resolutions
• Remote Database Cloud Isolation: - Blocker: Railway private DNS was unreachable from external Render backend. - Resolution: Enabled public TCP proxy endpoints and configured resilient connection pooling (mysql2/promise). • Cross-Origin & Environment Sync: - Blocker: Browser CORS policies blocked Vercel requests to Render API in production. - Resolution: Configured dynamic CORS whitelist & injected VITE_API_URL environment build variables. • Cross-Canteen Query Latency: - Blocker: Comparing dishes across multiple canteens needed multiple table scans.
- Resolution: Indexed foreign keys and created an optimized comparison REST endpoint.
3. Remaining Features (W3 & W4)
• Week 3 Milestone (Upcoming): - Kitchen Staff Portal: Live order display board for chefs to accept orders and mark "Food Ready". - Estimated Wait Time calculation based on active kitchen load. - Student Loyalty Points & discount redemption engine at checkout. • Week 4 Milestone (Upcoming): - Automated 30-min No-Show penalty & 3-strike account blocking system. - Canteen Admin Sales Analytics & revenue charts. - System Stress Testing & Final Viva Defense preparation. ★ Faculty Feedback & Guidance: - Integrating any additional suggestions recommended today.